## Package-22
PROPOSAL FOR STRENGTHENING OF ELECTRICAL NETWORK TO AVOID ELECTROCUTION OF ELEPHANTS UNDER MAYURBHANJ DISTRICT
SL No. | Forest Division | Forest Range | Forest Section | Forest Beat | Electrical Division | Electrical Section | Village | Stretch of transmission lines in Km. | GPS coordinates |  | Proposed Scope of Work
[9 empty] | Geo-Coordinate |  | LT Interposing Pole(With 9mtr RS Joist) ( in No.) | 3-Ph LT AB Cable (4x50+1x35+1x16mm2) ( in Km) | Fixing of 16mm LT Stay ( in Set) | 11 KV Interposing as per field requirement ( in No.) |  |  | 33KV Interposing as per field requirement ( in No.) |  |  | 11KV Insulated Conductor (99sqmm) in CKm | Fixing of 18mm HT Stay ( in Set) | Couping of Pole in No. | Fencing of Sub-station(in No.) | Spike (2nos. Per set per Pole) in Set | VCB
[9 empty] | Latitude | Longitude |  |  |  | 9 mtr RS Joist | 10 mtr Joist | 11 mtr Joist | 10 mtr Joist | 11 mtr Joist | 13 mtr RS Joist | [5 empty] | 33KV | 11KV
1 | Rairangpur | Badampahar | Badampahar | Badampahar | RED,Rairangpur | Kusumi | Nangalsila | 0.05 | 220 10' 7.7" | 860 13' 10.9" | 0 |  |  | 15 | [6 empty] | 4 |  |  | 30
2 | Rairangpur | Badampahar | Badampahar | Badampahar | RED,Rairangpur | Kusumi | Nangalsila | 0.2 | 220 10 '3.4" | 860 13' 8.4" | 10 | 0.5 | [11 empty] | 0
3 | Rairangpur | Badampahar | Badampahar | Badampahar | RED,Rairangpur | Kusumi | Ukam | 0.6 | 220 9' 37.2" | 860 11' 54.4" | 2 |  |  |  |  | 18 |  |  |  |  | 5 |  | 18 | 36
4 | Rairangpur | Badampahar | Badampahar | Badampahar | RED,Rairangpur | Kusumi | Dantusahi | 0.4 | 220 9' 23.6" | 860 12' 53.1" | 3 |  | 2 | [10 empty] | 0
5 | Rairangpur | Badampahar | Badampahar | Badampahar | RED,Rairangpur | Kusumi | Jagannathpur | 0.015 | 220 7' 16.6" | 860 12' 56.9" | 4 |  | 3 |  | 10 |  |  |  |  | 0.6 | 4 | 10 | 2 | 20
6 | Rairangpur | Badampahar | Suleipat | Jamjhari | RED,Rairangpur | Kusumi | Bodajodi | 0.3 | 220 6' 51.2" | 860 12' 20.7" | 5 |  | 4 |  | 15 |  |  |  |  | 1.5 | 9 | 15 | 2 | 30 |  | 1
7 | Rairangpur | Badampahar | Suleipat | Jamjhari | RED,Rairangpur | Kusumi | Patijhari | 0.3 | 220 5' 40.9" | 860 11' 56.4" | 7 |  | 6 |  | 13 |  |  |  |  | 1.3 | 7 | 13 | 2 | 26
8 | Rairangpur | Badampahar | Hatbadra | Hatbadra | RED,Rairangpur | Kusumi | Sarapoda | 0.33 | 220 7' 46.1" | 860 6' 40" |  |  |  |  | 26 |  |  |  |  | 1.5 | 6 |  |  | 52
9 | Rairangpur | Badampahar | Badampahar | Talapati | RED,Rairangpur | Kusumi | Jhipabandh | 2 | 220 4' 33.2" | 860 4' 27.5" |  |  |  | 24 | [6 empty] | 10 |  |  | 48
10 | Rairangpur | Badampahar | Badampahar | Talapati | RED,Rairangpur | Kusumi | Kathbharia | 0.4 | 220 5' 6.6" | 860 2' 12.8" |  |  |  |  | 20 | [5 empty] | 8 |  |  | 40
11 | Rairangpur | Badampahar | Badampahar | Talapati | RED,Rairangpur | Kusumi | Dhadichua | 1.5 | 220 4' 10" | 860 2' 21.4" | 7 |  | 2 | [10 empty] | 0
12 | Rairangpur | Badampahar | Badampahar | Talapati | RED,Rairangpur | Kusumi | Jhatisiring | 1.3 | 220 5' 9.9" | 860 0' 36.4" | 2 | [12 empty] | 0
13 | Rairangpur | Badampahar | Badampahar | Talapati | RED,Rairangpur | Kusumi | Pahadpur | 0.6 | 220 8' 42.5" | 860 1' 22.5" | 0 | [12 empty] | 0
14 | Rairangpur | Badampahar | Badampahar | Talapati | RED,Rairangpur | Kusumi | Banduda | 0.7 | 220 7' 58.5" | 860 0'48.8" | 3 |  | 2 | [10 empty] | 0
15 | Rairangpur | Badampahar | Badampahar | Purunapani | RED,Rairangpur | Kusumi | Ghusuria | 0.4 | 220 6' 20.5" | 860 9' 48.2" | 0 | [12 empty] | 0
16 | Rairangpur | Rairangpur | Badamtalia | Bijatala | RED,Rairangpur | Bisoi | Bankati to Jojosahi pole band | 0.5 | 220 11' 3.4" | 860 14' 48.7" |  |  |  |  | 28 |  |  |  |  | 1.2 | 12 | 28 | 4 | 56
17 | Rairangpur | Rairangpur | Badamtalia | Bijatala | RED,Rairangpur | Bisoi | Baliadhipa | 0.4 | 220 11' 57.1" | 860 14' 25.4" | 5 |  | 3 |  | 9 |  |  |  |  | 0.7 | 3 | 9 | 2 | 18
18 | Rairangpur | Rairangpur | Badamtalia | Bijatala | RED,Rairangpur | Bisoi | Balikotha | 0.5 | 220 10' 21.5" | 860 14' 23.7" | 6 |  |  |  | 10 |  |  |  |  | 0.9 | 5 | 10 | 2 | 20 |  | 1
19 | Rairangpur | Rairangpur | Badamtalia | Bijatala | RED,Rairangpur | Bisoi | Karkachia | 0.6 | 220 11' 21.5" | 860 15' 9.4" | 8 |  |  |  | 16 |  |  |  |  | 1.6 | 7 | 16 | 3 | 32
20 | Rairangpur | Rairangpur | Badamtalia | Bijatala | RED,Rairangpur | Bisoi | Bijatala near River | 0.5 | 220 12' 7" | 860 18' 25.7" | [5 empty] | 10 |  |  |  |  | 4 | 10 |  | 20
21 | Rairangpur | Rairangpur | Badamtalia | Bijatala | RED,Rairangpur | Bisoi | Bijatala back side of Medical | 0.6 | 220 12' 24.3" | 860 17' 45.7" | [5 empty] | 12 |  |  |  |  | 7 | 12 |  | 24
22 | Rairangpur | Rairangpur | Badamtalia | Bijatala | RED,Rairangpur | Bisoi | Teltangia | 0.4 | 220 11' 29.6" | 860 18' 15.4" | 6 |  | 3 |  |  | 8 |  |  |  | 0.8 | 4 | 8 | 1 | 16
23 | Rairangpur | Rairangpur | Badamtalia | Luhasila | RED,Rairangpur | Bisoi | Patpur near Nalla | 0.3 | 220 14' 27.2" | 860 14' 27.2" | [5 empty] | 10 |  |  |  |  | 4 | 10 | 2 | 20
24 | Rairangpur | Rairangpur | Badamtalia | Luhasila | RED,Rairangpur | Bisoi | Patpur near canal Side | 0.2 | 220 14' 30.2" | 860 18' 46.6" | [5 empty] | 9 |  |  |  |  | 3 | 9 | 1 | 18 |  | 1
25 | Rairangpur | Rairangpur | Badamtalia | Luhasila | RED,Rairangpur | Bisoi | Luhasila Canal Side | 0.15 | 220 14' 22" | 860 18' 45.3" | [5 empty] | 10 |  |  |  | 0.8 | 4 | 10 | 2 | 20
26 | Rairangpur | Rairangpur | Badamtalia | Luhasila | RED,Rairangpur | Bisoi | Luhasila Main Road | 0.4 | 220 14' 23.2" | 860 18' 53.8" | 4 | 0.4 | 3 | [10 empty] | 0
27 | Rairangpur | Rairangpur | Badamtalia | Luhasila | RED,Rairangpur | Bisoi | Luhasila Near Hospital | 0.5 | 220 14' 24.9" | 860 19' 13.9" | 6 | 0.5 | 4 |  |  | 5 |  |  |  | 0.5 | 2 | 5 | 2 | 10
28 | Rairangpur | Rairangpur | Badamtalia | Luhasila | RED,Rairangpur | Bisoi | Khejuri | 0.2 | 220 15' 6.8" | 860 20' 33.6" | 3 |  | 2 |  | 5 |  |  |  |  | 0.5 | 2 | 5 | 1 | 10
29 | Rairangpur | Rairangpur | Badamtalia | Luhasila | RED,Rairangpur | Bisoi | Khejuri near pond | 0.015 | 220 15' 25.5" | 860 20' 26" |  |  |  |  | 5 |  |  |  |  | 0.4 | 2 | 5 | 1 | 10
30 | Rairangpur | Rairangpur | Badamtalia | Luhasila | RED,Rairangpur | Bisoi | Arjunpani Main Road-I | 0.1 | 220 16' 51.7" | 860 20' 49" |  |  |  |  | 4 |  |  |  |  | 0.3 |  | 4 | 1 | 8
31 | Rairangpur | Rairangpur | Badamtalia | Luhasila | RED,Rairangpur | Bisoi | Arjunpani Main Road-II | 0.1 | 220 17' 2.3" | 860 20' 49.8" |  |  |  |  | 5 |  |  |  |  | 0.4 | 1 | 5 | 1 | 10
32 | Rairangpur | Rairangpur | Badamtalia | Luhasila | RED,Rairangpur | Bisoi | Arjunpani Main Road-III | 0.1 | 220 17' 18.7" | 860 20' 54.6" |  |  |  |  | 6 |  |  |  |  | 0.5 | 2 | 6 |  | 12
[8 empty] | 14.66 | 0 | 0 | 81 | 1.4 | 34 | 39 | 172 | 82 | 0 | 0 | 0 | 13.5 | 115 | 190 | 47 | 586 | 0 | 3

## Package-23
PROPOSAL FOR STRENGTHENING OF ELECTRICAL NETWORK TO AVOID ELECTROCUTION OF ELEPHANTS UNDER MAYURBHANJ DISTRICT
SL No. | Forest Division | Forest Range | Forest Section | Forest Beat | Electrical Division | Electrical Section | Village | Stretch of transmission lines in Km. | GPS coordinates |  | Proposed Scope of Work
[9 empty] | Geo-Coordinate |  | LT Interposing Pole(With 9mtr RS Joist) ( in No.) | 3-Ph LT AB Cable (4x50+1x35+1x16mm2) ( in Km) | Fixing of 16mm LT Stay ( in Set) | 11 KV Interposing as per field requirement ( in No.) |  |  | 33KV Interposing as per field requirement ( in No.) |  |  | 11KV Insulated Conductor (99sqmm) in CKm | Fixing of 18mm HT Stay ( in Set) | Couping of Pole in No. | Fencing of Sub-station(in No.) | Spike (2nos. Per set per Pole) in Set | VCB
[9 empty] | Latitude | Longitude |  |  |  | 9 mtr RS Joist | 10 mtr Joist | 11 mtr Joist | 10 mtr Joist | 11 mtr Joist | 13 mtr RS Joist | [5 empty] | 33KV | 11KV
1 | Rairangpur | Rairangpur | Badamtalia | Luhasila | RED,Rairangpur | Bisoi | Kuli | 0.15 | 220 15' 50.5" | 860 19' 54.8"
2 | Rairangpur | Manada | Manada | Alhapani | RED,Rairangpur | Bisoi | Budhikhamari | 0.15 | 220 7' 50.2" | 860 23' 40.1" | 6 | 0.8 | 5
3 | Rairangpur | Manada | Manada | Alhapani | RED,Rairangpur | Bisoi | Budhikhamari | 0.05 | 220 7' 36.5" | 860 23' 46" |  |  |  |  | 8 |  |  |  |  | 0.4 | 5 | 8 | 2 | 16
4 | Rairangpur | Manada | Manada | Sansialiani | RED,Rairangpur | Bisoi | Begunia | 0.06 | 220 59' 44.7" | 860 8' 45.6" | [13 empty] | 0
5 | Rairangpur | Manada | Manada | Sansialiani | RED,Rairangpur | Bisoi | Bankati | 0.18 | 220 1' 47.4" | 860 11' 3.3" | [13 empty] | 0
6 | Rairangpur | Manada | Manada | Tulasibani | RED,Rairangpur | Bisoi | Tulasibani | 0.15 | 220 57' 59.3" | 860 9' 24.7" | [13 empty] | 0
7 | Rairangpur | Bisoi | Bankidihi | Bankidihi | RED,Rairangpur | Bisoi | Raikadkacha | 0.03 | 220 5' 23.3" | 860 16' 51.6" | 3 |  | 2 |  | 6 |  |  |  |  | 0.9 | 5 | 6 | 1 | 12
8 | Rairangpur | Bisoi | Bisoi | Bisoi | RED,Rairangpur | Bisoi | Keshargadia | 0.1 | 220 11' 23.3" | 860 14' 11.5" | 5 |  | 2 |  | 6 |  |  |  |  | 0.3 | 3 | 6 | 1 | 12
9 | Rairangpur | Bisoi | Bisoi | Bisoi | RED,Rairangpur | Bisoi | Sagjodi | 0.1 | 220 10' 8.2" | 860 23' 51.6" | 8 |  | 5 | [10 empty] | 0
10 | Rairangpur | Bisoi | Bisoi | Bisoi | RED,Rairangpur | Bisoi | Sagjodi | 0.1 | 220 10' 14.4" | 860 23' 50" |  |  |  |  | 6 |  |  |  |  | 0.5 | 4 | 6 | 1 | 12
11 | Rairangpur | Bisoi | Bisoi | Bisoi | RED,Rairangpur | Bisoi | Sagjodi | 0.1 | 220 10' 21.5" | 860 23' 49.9" | 7 | 0.9 | 6 |  | 7 | [5 empty] | 3 | 9 | 2 | 14
12 | Rairangpur | Bisoi | Bisoi | Bisoi | RED,Rairangpur | Bisoi | Saraspada | 0.1 | 220 11' 53.9" | 860 23' 28.2" | 12 |  | 8 |  | 9 |  |  |  |  | 1.5 | 7 | 11 | 4 | 18
13 | Rairangpur | Bisoi | Bisoi | Bisoi | RED,Rairangpur | Bisoi | Nuadihi | 0.1 | 220 8' 50" | 860 19' 53.6" | 8 | 1.2 | 12 |  |  | 10 |  |  |  |  | 9 | 12 | 4 | 20
14 | Rairangpur | Bisoi | Bisoi | Bisoi | RED,Rairangpur | Bisoi | Sunajodia | 0.1 | 220 12' 9.4" | 860 12' 9.3" | 7 |  | 5 |  | 6 | 6 |  |  |  | 1.2 | 8 | 12 | 3 | 24
15 | Rairangpur | Bisoi | Bisoi | Gargadi | RED,Rairangpur | Bisoi | Kundulia | 0.1 | 220 10' 10.4" | 860 23' 4.4" | 6 | 0.9 | 12 |  | 6 | [5 empty] | 2 | 5 | 3 | 12
16 | Rairangpur | Bisoi | Bisoi | Gargadi | RED,Rairangpur | Bisoi | Kunjakacha | 0.1 | 220 12' 24.7" | 860 22' 29.5" | 6 |  |  |  | 9 | 8 |  |  |  | 1.9 | 9 | 17 | 2 | 34
17 | Rairangpur | Bisoi | Bisoi | Gargadi | RED,Rairangpur | Bisoi | Paunsia | 0.1 | 220 13' 24" | 860 21' 39.3" | 4 |  |  |  | 5 | 5 |  |  |  | 1.3 | 5 | 10 | 2 | 20
18 | Rairangpur | Bisoi | Rajabasa | Rajabasa | RED,Rairangpur | Bisoi | Rajabasa | 0.1 | 220 10' 45" | 860 28' 1" | 2 |  |  |  | 4 | 3 |  |  |  | 0.5 | 4 | 10 | 2 | 14 | 1 | 1
19 | Rairangpur | Bisoi | Rajabasa | Deopatta | RED,Rairangpur | Bisoi | Deopatta | 0.2 | 220 10' 30.3" | 860 28' 10.3" | 4 |  | 3 |  | 6 | 6 |  |  |  | 1.2 | 8 | 12 | 3 | 24
20 | Rairangpur | Bisoi | Rajabasa | Deopatta | RED,Rairangpur | Bisoi | Kitabeda | 0.5 | 220 9' 38.3" | 860 25' 55.9" | 5 |  | 4 |  |  | 18 |  |  |  | 2.5 | 12 | 18 | 3 | 36
21 | Rairangpur | Bisoi | Rajabasa | Dudhkundi | RED,Rairangpur | Bisoi | Near Khadambeda G.P. Office | 0.1 | 220 10' 34.6" | 860 26' 36.2" | 2 |  | 3 | 2 | 5 | 5 |  |  |  | 1.2 | 6 | 14 | 2 | 24
22 | Rairangpur | Bisoi | Rajabasa | Dudhkundi | RED,Rairangpur | Bisoi | Dakchati Jungle | 0.2 | 220 10' 10.7" | 860 25' 56.9" | [5 empty] | 12 |  |  |  | 0.6 | 8 | 12 | 2 | 24
[8 empty] | 2.87 | 0 | 0 | 85 | 3.8 | 67 | 2 | 83 | 73 | 0 | 0 | 0 | 14 | 98 | 168 | 37 | 316 | 1 | 1

## Package-24
PROPOSAL FOR STRENGTHENING OF ELECTRICAL NETWORK TO AVOID ELECTROCUTION OF ELEPHANTS UNDER MAYURBHANJ DISTRICT
SL No. | Forest Division | Forest Range | Forest Section | Forest Beat | Electrical Division | Electrical Section | Village | Stretch of transmission lines in Km. | GPS coordinates |  | Proposed Scope of Work
[9 empty] | Geo-Coordinate |  | LT Interposing Pole(With 9mtr RS Joist) ( in No.) | 3-Ph LT AB Cable (4x50+1x35+1x16mm2) ( in Km) | Fixing of 16mm LT Stay ( in Set) | 11 KV Interposing as per field requirement ( in No.) |  |  | 33KV Interposing as per field requirement ( in No.) |  |  | 11KV Insulated Conductor (99sqmm) in CKm | Fixing of 18mm HT Stay ( in Set) | Couping of Pole in No. | Fencing of Sub-station(in No.) | Spike (2nos. Per set per Pole) in Set | VCB
[9 empty] | Latitude | Longitude |  |  |  | 9 mtr RS Joist | 10 mtr Joist | 11 mtr Joist | 10 mtr Joist | 11 mtr Joist | 13 mtr RS Joist | [5 empty] | 33KV | 11KV
1 | Rairangpur | Bahalda | Jamda | Manbir | RED,Rairangpur | Rairangpur | Tarana | 0.1 | 220 15' 53.4" | 860 1' 44.3" |  |  |  | 6 | [5 empty] | 1.5 |  |  | 25 | 12
2 | Rairangpur | Bahalda | Jamda | Manbir | RED,Rairangpur | Rairangpur | Bhadusahi | 0.05 | 220 14' 59.7" | 860 1' 57.3" |  |  |  | 5 | [8 empty] | 15 | 10
3 | Rairangpur | Bahalda | Jamda | Jamda | RED,Rairangpur | Rairangpur | Rumapahadi | 0.3 | 220 14' 29.3" | 860 4' 1.4" |  |  |  | 11 | [6 empty] | 4 |  | 35 | 22
4 | Rairangpur | Bahalda | Jamda | Jamda | RED,Rairangpur | Rairangpur | Rumapahadi to Deukundi | 1 | 220 15' 7" | 860 3' 39.5" | 3 |  |  | 3 | [5 empty] | 0.5 | 2 |  |  | 6
5 | Rairangpur | Bahalda | Jamda | Sunamora | RED,Rairangpur | Rairangpur | Matiali to Jatapani | 0.4 | 220 13' 15.2" | 860 4' 32.8" | 5 | 0.6 |  | 11 | [5 empty] | 0.9 | 3 |  | 13 | 22
6 | Rairangpur | Bahalda | Jamda | Sunamora | RED,Rairangpur | Rairangpur | Dhalpur to Khairpal | 1 | 220 13' 30.2" | 860 5' 52.2" | 3 |  |  | 4 |  |  |  | 2 |  | 1.5 |  |  |  | 12
7 | Rairangpur | Bahalda | Jamda | Sunamora | RED,Rairangpur | Rairangpur | Dhalpur to Bhaleidihi | 1 | 220 13' 30.9 | 860 5' 56.6" | 2 |  |  | 4 |  |  |  | 2 |  | 0.8 | 3 |  | 4 | 12
8 | Rairangpur | Bahalda | Jamda | Sunamora | RED,Rairangpur | Rairangpur | Dumadihi | 0.3 | 220 14' 55.4" | 860 6' 32" | 2 |  |  | 3 | [5 empty] | 0.2 |  |  |  | 6
9 | Rairangpur | Bahalda | Jamda | Sunamora | RED,Rairangpur | Rairangpur | Dumadihi | 0.5 | 220 14' 55.2" | 860 6' 32.3" | 2 |  |  | 4 | [5 empty] | 0.2 |  |  |  | 8
10 | Rairangpur | Bahalda | Jamda | Sunamora | RED,Rairangpur | Rairangpur | Khairpal (Bakrasahi) | 0.2 | 220 14' 7" | 860 6' 19" | 2 | 0.5 |  | 3 | [9 empty] | 6
11 | Rairangpur | Bahalda | Jamda | Sunamora | RED,Rairangpur | Rairangpur | MatialiChhak | 0.5 | 220 13' 12.3" | 860 4' 32.7" |  |  |  | 3 |  |  |  | 4 |  | 0.5 |  |  | 4 | 14
12 | Rairangpur | Bahalda | Jamda | Jamda | RED,Rairangpur | Rairangpur | Jamda to Heselpata | 0.2 | 220 17' 14.6" | 860 2' 39.6" | 11 | 0.8 | [5 empty] | 10 |  |  |  |  | 10 | 20
13 | Rairangpur | Bahalda | Jamda | Jamda | RED,Rairangpur | Rairangpur | Pasna | 0.2 | 220 17' 32.6" | 860 3' 45.5" | 11 | 0.9 |  | 7 | [5 empty] | 0.5 |  |  | 7 | 14
14 | Rairangpur | Bahalda | Jamda | Jamda | RED,Rairangpur | Rairangpur | Madhupur | 0.8 | 220 14' 10.6" | 860 2' 29.8" |  |  |  | 9 | [9 empty] | 18
15 | Rairangpur | Bahalda | Jamda | Jamda | RED,Rairangpur | Rairangpur | Madhupur | 0.6 | 220 14' 18" | 860 2' 29.1" | 4 | 0.4 | [11 empty] | 0
16 | Rairangpur | Bahalda | Jamda | Sunamora | RED,Rairangpur | Rairangpur | Basantpur | 0.3 | 220 12' 39.3" | 860 5' 58.5" | [7 empty] | 5 |  | 0.5 |  |  |  | 10
17 | Rairangpur | Bahalda | Jamda | Manbir | RED,Rairangpur | Rairangpur | Manbir | 0.2 | 220 16' 22.9" | 860 0' 26.9" |  |  |  | 4 | [9 empty] | 8
18 | Rairangpur | Bahalda | Jamda | Jamda | RED,Rairangpur | Rairangpur | Bandudumanala | 0.1 | 220 16' 50.5" | 860 4' 27.9" | [7 empty] | 3 |  | 0.6 |  |  |  | 6
19 | Rairangpur | Bahalda | Jamda | Jamda | RED,Rairangpur | Rairangpur | Bhadusahi (San Sahi) | 0.3 | 220 15' 57.1" | 860 12' 35.8" |  |  |  | 7 | [5 empty] | 0.6 |  |  |  | 14
20 | Rairangpur | Bahalda | Jamda | Sunamora | RED,Rairangpur | Rairangpur | Matiali to Basantpur | 0.1 | 220 13' 3.1" | 860 5' 14.8" |  |  |  | 12 | [5 empty] | 0 |  |  |  | 24
21 | Rairangpur | Bahalda | Bahalda | Tiring | RED,Rairangpur | Bahalda | Changua(Cable wire) | 0.1 | 220 30' 48.7" | 860 1' 38.5" | 3 | 0.35 | [11 empty] | 0
22 | Rairangpur | Bahalda | Bahalda | Tiring | RED,Rairangpur | Bahalda | Changua(DP Boring) | 0.05 | 220 31' 12" | 860 1' 41" | 2 |  |  | 4 | [5 empty] | 0 |  |  |  | 8
23 | Rairangpur | Bahalda | Bahalda | Tiring | RED,Rairangpur | Bahalda | Bankati (Cable Wire) | 0.3 | 220 30' 23.2" | 860 2' 6.9" |  |  |  |  | 6 |  |  |  |  | 0.31 | 2 |  |  | 12
24 | Rairangpur | Bahalda | Bahalda | Tiring | RED,Rairangpur | Bahalda | Charkadihi | 1 | 220 28' 12.3" | 860 5' 6.5" | 3 |  |  |  | 4 |  |  |  |  | 0.25 |  |  |  | 8
25 | Rairangpur | Bahalda | Bahalda | Bahalda | RED,Rairangpur | Bahalda | Gambharia To Brahmanbose | 1 | 220 11' 52" | 860 5' 16.9" | 5 | 5 | 4 | 3 |  | 2 |  |  |  | 3 | 1 |  | 12 | 10
26 | Rairangpur | Bahalda | Jharadihi | Jharadihi | RED,Rairangpur | Bahalda | Jharadihi to Majhigan | 0.4 | 220 26' 34.7" | 860 9' 47" |  |  |  |  | 7 | [5 empty] | 2 |  |  | 14
27 | Rairangpur | Rairangpur | Badamtalia | Khanta | RED,Rairangpur | Kantabani | Mundathakura (In front of School) | 0.4 | 220 13' 35.9" | 860 15' 35.4" |  |  |  |  | 10 |  |  |  |  | 0.9 | 5 | 10 | 2 | 20
28 | Rairangpur | Rairangpur | Badamtalia | Khanta | RED,Rairangpur | Kantabani | Khanta Bazar | 0.5 | 220 14' 28.2" | [14 empty] | 0
29 | Rairangpur | Rairangpur | Badamtalia | Khanta | RED,Rairangpur | Kantabani | Kaliakpur | 0.6 | 220 14' 28.2" | 860 15' 17.8" | [5 empty] | 20 |  |  |  | 1.6 | 6 | 20 | 2 | 40
30 | Rairangpur | Rairangpur | Badamtalia | Khanta | RED,Rairangpur | Kantabani | Badjharan Main Road-I | 0.5 | 220 14' 49.7" | 860 15' 40.8" | 3 |  | 4 |  | 10 |  |  |  |  | 0.8 | 5 | 10 | 1 | 20
31 | Rairangpur | Rairangpur | Badamtalia | Khanta | RED,Rairangpur | Kantabani | Badjharan Main Road-II | 0.4 | 220 14' 50.3" | 860 15' 44.1" | 2 |  | 3 |  | 9 |  |  |  |  | 0.7 | 3 | 9 | 1 | 18
32 | Rairangpur | Rairangpur | Badamtalia | Khanta | RED,Rairangpur | Kantabani | Judia | 0.4 | 220 14' 45" | 860 15' 19.5" | 5 | 0.6 | 4 |  | 11 |  |  |  |  | 1.1 | 4 | 11 | 2 | 22
33 | Rairangpur | Rairangpur | Badamtalia | Khanta | RED,Rairangpur | Kantabani | Bhalujudi(and of Village) | 0.2 | 220 14' 45.4" | 860 16' 21" | 3 | 0.4 | 6 |  | 6 |  |  |  |  | 0.7 | 3 | 6 | 2 | 12
34 | Rairangpur | Rairangpur | Badamtalia | Khanta | RED,Rairangpur | Kantabani | Bhalujodi in front of holler | 0.05 | 220 14' 15.5" | 860 17' 37.5" | 2 |  |  |  | 4 |  |  |  |  | 0.4 | 2 | 4 | 2 | 8
35 | Rairangpur | Rairangpur | Badamtalia | Khanta | RED,Rairangpur | Kantabani | AmdihaNalla | 0.1 | 220 14' 46.3" | 860 16' 1.6" |  |  |  |  | 6 |  |  |  |  | 0.4 | 3 | 6 |  | 12
36 | Rairangpur | Rairangpur | Badamtalia | Khanta | RED,Rairangpur | Kantabani | BudhiakudarNalla | 0.3 | 220 14' 55.1" | 860 11' 42.1" | [7 empty] | 12 |  |  | 14 | 12 |  | 24
37 | Rairangpur | Rairangpur | Gorumahisani | Chhatramandal | RED,Rairangpur | Kantabani | Bhimkhanda-1 | 0.15 | 220 18' 36.9" | 860 21' 1.7" | [13 empty] | 0
38 | Rairangpur | Rairangpur | Gorumahisani | Chhatramandal | RED,Rairangpur | Kantabani | Bhimkhanda-2 | 0.1 | 220 18' 57.1" | 860 21' 5.2" | [13 empty] | 0
39 | Rairangpur | Rairangpur | Gorumahisani | Chhatramandal | RED,Rairangpur | Kantabani | Bhimkhanda-3 | 0.12 | 220 18' 55.3" | 860 21' 20.6" | [13 empty] | 0
40 | Rairangpur | Rairangpur | Gorumahisani | Gorumahisani | RED,Rairangpur | Kantabani | Jari Hill | 0.35 | 220 19' 31.6" | 860 17' 50.6" | [13 empty] | 0
[8 empty] | 15.17 | 0 | 0 | 73 | 9.55 | 21 | 103 | 73 | 22 | 0 | 38 | 0 | 18.46 | 62 | 88 | 137 | 472 | 0 | 0

## Package-25
PROPOSAL FOR STRENGTHENING OF ELECTRICAL NETWORK TO AVOID ELECTROCUTION OF ELEPHANTS UNDER MAYURBHANJ DISTRICT
SL No. | Forest Division | Forest Range | Forest Section | Forest Beat | Electrical Division | Electrical Section | Village | Stretch of transmission lines in Km. | GPS coordinates |  | Proposed Scope of Work
[9 empty] | Geo-Coordinate |  | LT Interposing Pole(With 9mtr RS Joist) ( in No.) | 3-Ph LT AB Cable (4x50+1x35+1x16mm2) ( in Km) | Fixing of 16mm LT Stay ( in Set) | 11 KV Interposing as per field requirement ( in No.) |  |  | 33KV Interposing as per field requirement ( in No.) |  |  | 11KV Insulated Conductor (99sqmm) in CKm | Fixing of 18mm HT Stay ( in Set) | Couping of Pole in No. | Fencing of Sub-station(in No.) | Spike (2nos. Per set per Pole) in Set | VCB
[9 empty] | Latitude | Longitude |  |  |  | 9 mtr RS Joist | 10 mtr Joist | 11 mtr Joist | 10 mtr Joist | 11 mtr Joist | 13 mtr RS Joist | [5 empty] | 33KV | 11KV
1 | Karanjia | Karanjia | Singda | Singda | RED, Rairangpur | Karanjia-II | Budhisorei | 1 | 21° 49' 65.22" E | 85° 55' 29.35"N | 5 | 1.2 | 12 |  | 18 |  |  |  |  | 1.5 | 15 | 30 | 2 | 36 |  | 2
2 | Karanjia | Dudhiani | Ranipat | Ranipat | RED, Rairangpur | Karanjia-II | Malharpoda | 2.5 | 21° 52' 18.0" E | 86° 03' 36.1"N | 22 | 2 | 10 |  | 16 |  |  |  |  | 2.5 | 20 | 25 | 2 | 32 |  | 1
3 | Karanjia | Dudhiani | Ranipat | Ranipat | RED, Rairangpur | Karanjia-II | Sanagan | 2 | 21° 52' 06.1" E | 86° 04' 17.7"N | 14 | 1.5 | 8 |  | 15 |  |  |  |  | 2 | 24 | 20 | 2 | 30
4 | Karanjia | Dudhiani | Tato | Tato | RED, Rairangpur | Karanjia-II | Nodhagadia | 1.6 | 21° 52' 25.7" E | 86° 03' 04.1"N | 12 | 1.1 | 10 |  | 16 |  |  |  |  | 1.2 | 15 | 25 | 4 | 32
5 | Karanjia | Dudhiani | Barakamuda | Hatibari | RED, Rairangpur | Karanjia-II | Hatibari | 1.4 | 21° 48' 27.9" E | 86° 04' 56.2"N | 18 | 1.5 | 15 |  | 15 |  |  |  |  | 2 | 35 | 45 | 3 | 30
6 | Karanjia | Dudhiani | Tato | Purunapani | RED, Rairangpur | Karanjia-II | Pechasahi | 1.8 | 21° 49' 19.8" E | 86° 03' 10.2"N | 25 | 1.8 | 20 |  | 22 |  |  |  | 2 | 1.5 | 30 | 40 | 5 | 48
7 | Karanjia | Dudhiani | Tato | Tato | RED, Rairangpur | Karanjia-II | Salarapada | 2 | 21° 49’ 19.8" E | 86° 02' 49.7"N | 26 | 2 | 25 |  | 25 |  |  |  | 2 | 1.8 | 40 | 30 | 3 | 54
8 | Karanjia | Dudhiani | Ranipat | Ranipat | RED, Rairangpur | Karanjia-II | Batagoudagan | 1.8 | 21° 52' 45.0" E | 86° 04' 11.9"N | 25 | 1.6 | 22 |  | 26 |  |  |  |  | 2 | 30 | 50 | 4 | 52
9 | Karanjia | Dudhiani | Tangabilla | Tangabilla | RED, Rairangpur | Karanjia-II | Tintia | 1.3 | 21° 52' 52.9" E | 86° 00' 12.5"N | 12 | 0.6 | 10 |  | 10 |  |  |  |  | 2 | 25 | 40 | 2 | 20
[8 empty] | 15.4 | 0 | 0 | 159 | 13.3 | 132 | 0 | 163 | 0 | 0 | 0 | 4 | 16.5 | 234 | 305 | 27 | 334 | 0 | 3

## Package-26
PROPOSAL FOR STRENGTHENING OF ELECTRICAL NETWORK TO AVOID ELECTROCUTION OF ELEPHANTS UNDER MAYURBHANJ DISTRICT
SL No. | Forest Division | Forest Range | Forest Section | Forest Beat | Electrical Division | Electrical Section | Village | Stretch of transmission lines in Km. | GPS coordinates |  | Proposed Scope of Work
[9 empty] | Geo-Coordinate |  | LT Interposing Pole(With 9mtr RS Joist) ( in No.) | 3-Ph LT AB Cable (4x50+1x35+1x16mm2) ( in Km) | Fixing of 16mm LT Stay ( in Set) | 11 KV Interposing as per field requirement ( in No.) |  |  | 33KV Interposing as per field requirement ( in No.) |  |  | 11KV Insulated Conductor (99sqmm) in CKm | Fixing of 18mm HT Stay ( in Set) | Couping of Pole in No. | Fencing of Sub-station(in No.) | Spike (2nos. Per set per Pole) in Set | VCB
[9 empty] | Latitude | Longitude |  |  |  | 9 mtr RS Joist | 10 mtr Joist | 11 mtr Joist | 10 mtr Joist | 11 mtr Joist | 13 mtr RS Joist | [5 empty] | 33KV | 11KV
1 | Karanjia | Karanjia | Raruan | Raruan | RED, Rairangpur | SUKRULI | Jodipada | 1 | 21° 57' 31.7" E | 85° 49' 41.6"N | 8 | 1 | 6 |  | 15 | [5 empty] | 10 | 15 | 3 | 30
2 | Karanjia | Karanjia | Raruan | Raruan | RED, Rairangpur | SUKRULI | Tulasipur | 1 | 21° 57' 27.6" E | 85° 50' 25.1"N | 5 | 0.5 | 5 |  | 7 |  |  | 11 |  |  | 5 | 7 | 2 | 36
3 | Karanjia | Karanjia | Ghagarbeda | Naksara | RED, Rairangpur | SUKRULI | Naksara | 1 | 22° 06' 04.1" E | 85° 48' 24.0"N | 9 | 0.8 | 7 |  | 20 | [5 empty] | 12 | 20 | 2 | 40 |  | 1
4 | Karanjia | Karanjia | Ghagarbeda | Naksara | RED, Rairangpur | SUKRULI | Kudarsahi to Rangamatia | 1 | 22° 06' 02.9" E | 85° 47' 36.9"N | 8 | 0.7 | 5 |  | 18 | [5 empty] | 10 | 18 | 2 | 36
5 | Karanjia | Karanjia | Ghagarbeda | Naksara | RED, Rairangpur | SUKRULI | Rangamatia | 1 | 22° 05' 07.6" E | 85° 47' 19.3"N | 5 | 0.5 | 3 |  | 9 | [5 empty] | 4 | 9 | 1 | 18
7 | Karanjia | Thakurmunda | Champajhar | Champajhar | RED, Rairangpur | Thakurmunda | Champajhar | 1.5 | 21° 28' 57.0" E | 86° 12' 39.9"N | 60 | 1.7 | 15 |  | 22 | 18 |  |  |  | 1.5 | 20 | 40 | 5 | 80 |  | 1
8 | Karanjia | Thakurmunda | Champajhar | Champajhar | RED, Rairangpur | Thakurmunda | Mankadbeda | 2.5 | 21° 29' 11.1" E | 86° 14' 23.4"N | 18 | 1.5 | 12 |  | 22 |  |  |  |  | 1 | 6 | 22 | 1 | 44
9 | Karanjia | Thakurmunda | Champajhar | Champajhar | RED, Rairangpur | Thakurmunda | Nuagaon | 1.5 | 21° 29' 02.3" E | 86° 14' 16.4"N | 20 | 1.5 | 12 |  | 19 | 11 |  |  |  |  | 5 | 30 |  | 60
10 | Karanjia | Thakurmunda | Thakurmunda | Thakurmunda-I | RED, Rairangpur | Thakurmunda | Thakurmunda | 2 | 21° 31' 09.9" E | 86° 09' 14.2"N | 42 | 2 | 15 |  | 17 | 15 |  | 29 |  | 3 | 17 | 40 | 7 | 122
11 | Karanjia | Thakurmunda | Champajhar | Champajhar | RED, Rairangpur | Thakurmunda | Champajhar | 1.5 | 21° 28' 57" E | 86° 12' 39.9"N | [13 empty] | 0
12 | Karanjia | Thakurmunda | Thakurmunda | Thakurmunda-I | RED, Rairangpur | Thakurmunda | Jamunalia | 2 | 21° 32' 37.4" E | 86° 09' 55.8"N | 15 | 1.5 | 13 |  | 14 | 8 |  |  |  | 1.4 | 4 | 22 | 1 | 44
13 | Karanjia | Thakurmunda | Keshdiha | Mituani | RED, Rairangpur | Thakurmunda | Mituani | 2.1 | 21° 32' 32.7" E | 86° 11' 56.1"N | 19 | 2.1 | 8 |  | 11 | 4 |  |  |  |  | 5 | 15 | 1 | 30
14 | Karanjia | Thakurmunda | Thakurmunda | Thakurmunda-I | RED, Rairangpur | Thakurmunda | Baunsadiha | 1.8 | 21° 31' 35.7" E | 86° 07' 40.6"N | 15 | 1.8 | 8 |  | 18 | 6 |  |  |  |  | 6 | 24 | 1 | 48
15 | Karanjia | Thakurmunda | Keshdiha | Mituani | RED, Rairangpur | Thakurmunda | Baliposi | 1.8 | 21° 33' 41.6" E | 86° 12' 35.2"N | 14 | 1.8 | 6 |  | 10 | 9 |  |  |  |  | 2 | 19 |  | 38
24 | Karanjia | Satkosia | Satkosia | Satkosia | RED, Rairangpur | Thakurmunda | Gadasahi | 0.7 | 21° 21' 31.7" E | 86° 09' 07.6"N | 9 | 0.7 | 4 |  | 5 | 3 |  |  |  |  | 2 | 8 |  | 16
25 | Karanjia | Satkosia | Satkosia | Satkosia | RED, Rairangpur | Thakurmunda | Kasibahali | 0.6 | 21° 20' 59.9" E | 86° 08' 52.0"N | 8 | 0.6 | 3 |  | 15 | [5 empty] | 6 | 15 | 1 | 30
27 | Karanjia | Satkosia | Mahuldiha | Mahuldiha | RED, Rairangpur | Thakurmunda | Mahuldiha | 2 | 21° 26' 05.6" E | 86° 09' 52.9"N | 22 | 2 | 8 |  | 22 | 32 |  |  |  |  | 20 | 54 | 4 | 108
28 | Karanjia | Satkosia | Satkosia | Satkosia | RED, Rairangpur | Thakurmunda | Gadasahi | 0.7 | 21° 21' 31.7" E | 86° 09' 07.6"N | [13 empty] | 0
29 | Karanjia | Satkosia | Satkosia | Satkosia | RED, Rairangpur | Thakurmunda | Kasibahali | 0.5 | 21° 20' 59.9" E | 86° 08' 52.0"N | [13 empty] | 0
30 | Karanjia | Satkosia | Satkosia | Dhatikidiha | RED, Rairangpur | Thakurmunda | Godbhanga | 0.7 | 21° 19' 09.6" E | 86° 06' 44.9"N | [13 empty] | 0
34 | Karanjia | Gurguria | Bhanda | Pahadpur | RED, Rairangpur | JASHIPUR | Nouna (Majhi Sahi) | 3 | 22° 00' 17.1" E | 86° 00' 15.3"N | 20 | 1.5 | 8 |  | 20 | [5 empty] | 8 | 20 | 3 | 40
35 | Karanjia | Karanjia | Karanjia | Karanjia | RED, Rairangpur | Karanjia-I | Badadeuli | 0.35 |  |  | 6 | 0.35 | 4 |  | 8 |  |  |  |  | 1 | 5 | 14 |  | 16
[8 empty] | 30.25 | 0 | 0 | 303 | 22.55 | 142 | 0 | 272 | 106 | 0 | 40 | 0 | 7.9 | 147 | 392 | 34 | 836 | 0 | 2

## Package-27
PROPOSAL FOR STRENGTHENING OF ELECTRICAL NETWORK TO AVOID ELECTROCUTION OF ELEPHANTS UNDER KEONJHAR DISTRICT
SL No. | Forest Division | Forest Range | Forest Section | Forest Beat | Electrical Division | Electrical Section | Village | Stretch of transmission lines in Km. | GPS coordinates |  | Proposed Scope of Work
[9 empty] | Geo-Coordinate |  | LT Interposing Pole(With 9mtr RS Joist) ( in No.) | 3-Ph LT AB Cable (4x50+1x35+1x16mm2) ( in Km) | Fixing of 16mm LT Stay ( in Set) | 11 KV Interposing as per field requirement ( in No.) |  |  | 33KV Interposing as per field requirement ( in No.) |  |  | 11KV Insulated Conductor (99sqmm) in CKm | Fixing of 18mm HT Stay ( in Set) | Couping of Pole in No. | Fencing of Sub-station(in No.) | Spike (2nos. Per set per Pole) in Set | VCB
[9 empty] | Latitude | Longitude |  |  |  | 9 mtr RS Joist | 10 mtr Joist | 11 mtr Joist | 10 mtr Joist | 11 mtr Joist | 13 mtr RS Joist | [5 empty] | 33KV | 11KV
1 | Keonjhar | Keonjhar | Naranpur | Gopalpur(W) | KED,Keonjhar | RE-1 | Gopalpur | 0.2 | 21 34 06.9 | 85 42 07.5 |  |  |  |  | 2 |  |  |  |  | 0.22 |  | 2 |  | 4
2 | Keonjhar | Keonjhar | Naranpur | Gopalpur(W) | KED,Keonjhar | RE-1 | Gopalpur | 0.5 | 21 34 22.7 | 85 42 28.4 |  |  |  |  | 5 |  |  |  |  | 0.55 | 1 | 5 |  | 10
3 | Keonjhar | Keonjhar | Naranpur | Gopalpur(W) | KED,Keonjhar | RE-1 | Gopalpur | 0.2 | 21 45 16.8 | 85 38 58.8 |  |  |  |  | 2 |  |  |  |  | 0.22 |  | 2 |  | 4
4 | Keonjhar | Keonjhar | Naranpur | Gopalpur(W) | KED,Keonjhar | RE-1 | Gopalpur | 0.4 | 21 34 01.0 | 85 42 47.7 |  |  |  |  | 4 |  |  |  |  | 0.44 | 1 | 4 |  | 8
5 | Keonjhar | Keonjhar | Naranpur | Gopalpur(W) | KED,Keonjhar | RE-1 | Patana | 0.1 | 21 32 7.3 | 85 40 58.5 |  |  |  |  | 1 |  |  |  |  | 0.11 |  | 1 |  | 2
6 | Keonjhar | Keonjhar | Naranpur | Gopalpur(W) | KED,Keonjhar | RE-1 | Bathudi Sahi | 0.2 | 21 33 04.8 | 85 40 39.5 |  |  |  |  | 2 |  |  |  |  | 0.22 |  | 2 |  | 4
7 | Keonjhar | Keonjhar | Naranpur | Gopalpur(W) | KED,Keonjhar | RE-1 | Kandasar | 1.5 | 21 32 58.4 | 85 40 59.0 |  |  |  |  | 12 |  |  |  |  | 1.65 | 3 | 12 |  | 24
8 | Keonjhar | Keonjhar | Naranpur | Gopalpur(W) | KED,Keonjhar | RE-1 | Baradisahi | 0.5 | 21 33 18.6 | 85 41 37.3 |  |  |  |  | 5 |  |  |  |  | 0.55 |  | 5 |  | 10
9 | Keonjhar | Keonjhar | Naranpur | Naranpur | KED,Keonjhar | RE-1 | Ghutakeswarri | 0.1 | 21 36 32.2 | 85 38 59.3 |  |  |  |  | 1 |  |  |  |  | 0.11 |  | 1 |  | 2
10 | Keonjhar | Keonjhar | Naranpur | Naranpur | KED,Keonjhar | RE-1 | Ghutakeswarri | 0.2 | 21 36 22.8 | 85 39 01.6 |  |  |  |  | 2 |  |  |  |  | 0.22 |  | 2 |  | 4
11 | Keonjhar | Keonjhar | Naranpur | Naranpur | KED,Keonjhar | RE-1 | Ratna sahi | 0.1 | 21 35 29.7 | 85 39 08.3 |  |  |  |  | 1 |  |  |  |  | 0.11 |  | 1 |  | 2
12 | Keonjhar | Keonjhar | Naranpur | Naranpur | KED,Keonjhar | Sec-2 | Sirisipal | 0.5 | 21 35 10.4 | 85 37 39.9 |  |  |  |  | 5 | 2 |  |  |  | 0.55 | 1 | 5 |  | 14
13 | Keonjhar | Keonjhar | Naranpur | Naranpur | KED,Keonjhar | Sec-2 | Sirisipal | 0.2 | 21 35 25.1 | 85 37 34.3 |  |  |  |  | 2 | 1 |  |  |  | 0.22 | 5 | 2 |  | 6
14 | Keonjhar | Keonjhar | Naranpur | Naranpur | KED,Keonjhar | RE-1 | Dimboo | 0.1 | 21 35 25.1 | 85 37 34.3 |  |  |  |  | 1 |  |  |  |  | 0.11 |  | 1 |  | 2
15 | Keonjhar | Keonjhar | Naranpur | Naranpur | KED,Keonjhar | RE-1 | Dimboo | 0.1 | 2135 25.1 | 85 37 34.3 |  |  |  |  | 1 |  |  |  |  | 0.11 |  | 1 |  | 2
16 | Keonjhar | Keonjhar | Palaspanga | Raikala | KED,Keonjhar | Saharapada | Karanjiapada | 0.4 | 21 50 34.2 | 85 37 06.6 |  |  |  |  | 4 |  |  |  |  | 0.44 |  | 4 |  | 8
17 | Keonjhar | Keonjhar | Palaspanga | Kampodihi | KED,Keonjhar | RE-1 | Uparkampadihi | 0.4 | 21 42 27 | 85 29 05 |  |  |  |  | 4 |  |  |  |  | 0.44 |  | 4 |  | 8
18 | Keonjhar | Keonjhar | Palaspanga | Dhanurjaypur | KED,Keonjhar | RE-1 | Amrutpada | 0.2 | 21 46 1.08 | 85 31 5.57 |  |  |  |  | 2 |  |  |  |  | 0.22 |  | 2 |  | 4
19 | Keonjhar | Keonjhar | Palaspanga | Dhanurjaypur | KED,Keonjhar | RE-1 | Amrutapada Patala | 0.6 | 21 45 58.08 | 85 31 12.14 |  |  |  |  | 6 |  |  |  |  | 0.66 |  | 6 |  | 12
20 | Keonjhar | Keonjhar | Palaspanga | Dhanurjaypur | KED,Keonjhar | RE-1 | Amrutapada Patala | 0.8 | 21 45 57.70 | 85 31 26.51 |  |  |  |  | 8 |  |  |  |  | 0.88 | 2 | 8 |  | 16
21 | Keonjhar | Keonjhar | Palaspanga | Dhanurjaypur | KED,Keonjhar | Banspal | Kalanda | 0.2 | 21 46 12.96 | 85 31 30.89 |  |  |  |  | 2 |  |  |  |  | 0.22 |  | 2 |  | 4
22 | Keonjhar | Keonjhar | Palaspanga | Hatikucha | KED,Keonjhar | RE-1 | Poipani | 0.2 | 21 43 54.46 | 85 30 57.83 |  |  |  |  | 2 |  |  |  |  | 0.22 |  | 2 |  | 4
23 | Keonjhar | Keonjhar | Palaspanga | Hatikucha | KED,Keonjhar | RE-1 | Patna babu sahi | 0.4 | 21 45 13.2 | 85 31 15.4 |  |  |  |  | 4 |  |  |  |  | 0.44 |  | 4 |  | 8
24 | Keonjhar | Keonjhar | Town | Sidhmath | KED,Keonjhar | Sec-2 | Saras | 0.2 | 21 36 38.1 | 85 36 33.2 |  |  |  |  | 2 |  |  |  |  | 0.22 |  | 2 |  | 4
25 | Keonjhar | Keonjhar | Town | Sidhmath | KED,Keonjhar | Sec-2 | Balabhadrapur | 0.4 | 21 36 21.9 | 85 36 23.5 |  |  |  |  | 4 |  |  |  |  | 0.44 |  | 4 |  | 8
26 | Keonjhar | Keonjhar | Town | Sidhmath | KED,Keonjhar | Sec-2 | Badampati | 0.3 | 21 35 30.5 | 85 37 26.6 |  |  |  |  | 3 |  |  |  |  | 0.33 |  | 3 |  | 6
27 | Keonjhar | Keonjhar | Town | Sidhmath | KED,Keonjhar | Sec-2 | Badampati | 0.12 | 21 35 15.2 | 85 37 45.1 |  |  |  |  | 2 |  |  |  |  | 0.132 |  | 2 |  | 4
28 | Keonjhar | Keonjhar | Town | Sidhmath | KED,Keonjhar | Sec-3 | judia | 0.5 | 21 37 54.4 | 85 34 29.4 |  |  |  |  | 5 |  |  |  |  | 0.55 | 1 | 5 |  | 10
29 | Keonjhar | Keonjhar | Town | Belda | KED,Keonjhar | Sec-2 | Beloposhi | 0.15 | 21 41 24.4 | 85 40 37.2 |  |  |  |  | 2 |  |  |  |  | 0.16 | 2 | 2 |  | 4
30 | Keonjhar | Keonjhar | Town | Maidankel | KED,Keonjhar | RE-1 | Chaka nuasahi | 0.5 | 21 38 18.21 | 85 40 53.04 |  |  |  |  | 5 |  |  |  |  | 0.55 |  | 5 |  | 10
31 | Keonjhar | Keonjhar | Town | Maidankel | KED,Keonjhar | RE-1 | Baghua sahi | 0.3 | 21 40 15.28 | 85 42 6.17 |  |  |  |  | 3 |  |  |  |  | 0.33 |  | 3 |  | 6
32 | Keonjhar | Keonjhar | Janghira | Janghira(W) | KED,Keonjhar | RE-1 | Barsapal | 0.1 | 21 26 19.6 | 85 36 13.0 |  |  |  |  | 1 |  |  |  |  | 0.11 |  | 1 |  | 2
33 | Keonjhar | BJP | Kanjipani | Gandijoja | KED,Keonjhar | Banspal | Bayakumutia | 0.5 | 21 3218.40 | 85 29 51.9 |  |  |  |  | 5 |  |  |  |  | 0.55 |  | 5 |  | 10
34 | Keonjhar | BJP | Suakati | Anjar | KED,Keonjhar | Sec-3 | Anjar | 0.2 | 21 37 47.03 | 85 33 4.08 |  |  |  |  | 8 |  |  |  |  | 0.22 | 2 | 8 |  | 16
35 | Keonjhar | BJP | Suakati | Kaipur | KED,Keonjhar | Banspal | Kaipur | 0.4 | 21 34 10.4 | 85.29 29 53 |  |  |  |  | 4 |  |  |  |  | 0.44 |  | 4 |  | 8
36 | Keonjhar | BJP | Suakati | Suakati | KED,Keonjhar | Banspal | Suakati | 0.2 | 21 34 15 | 85 30 15.8 |  |  |  |  | 12 |  |  |  |  | 0.22 | 4 | 12 |  | 24 |  | 1
37 | Keonjhar | BJP | Kanjipani | Gandijoda | KED,Keonjhar | Banspal | Bayakumutia | 0.3 | 21 32 18.4 | 85 29 52 |  |  |  |  | 3 |  |  |  |  | 0.33 |  | 3 |  | 6
38 | Keonjhar | Patna | Patna | Tando | KED,Keonjhar | Patna | Dumuria | 0.06 | 21 34 23.9 | 85 58 37.8 |  |  |  |  | 1 |  |  |  |  | 0.07 |  | 1 |  | 2
39 | Keonjhar | Patna | Patna | Tando | KED,Keonjhar | Patna | Dumuria | 0.232 | 21 33 52.9 | 85 58 39.9 |  |  |  |  | 3 |  |  |  |  | 0.3 |  | 3 |  | 6
40 | Keonjhar | Patna | Patna | Tando | KED,Keonjhar | Patna | Dumuria | 0.16 | 21 33 57.6 | 85 58 43.3 |  |  |  |  | 2 |  |  |  |  | 0.18 |  | 2 |  | 4
41 | Keonjhar | Patna | Patna | Tando | KED,Keonjhar | Patna | Palanghati | 0.145 | 21 31 50.2 | 85 56 35.2 |  |  |  |  | 2 |  |  |  |  | 0.1595 |  | 2 |  | 4
42 | Keonjhar | Patna | Patna | Tando | KED,Keonjhar | Patna | Sadangabahali | 0.138 | 21 31 15.3 | 85 56 20.1 |  |  |  |  | 2 |  |  |  |  | 0.15 |  | 2 |  | 4
43 | Keonjhar | Patna | Patna | Tando | KED,Keonjhar | Patna | Pichhulabeda | 0.098 | 21 32 39.5 | 85 58 22.4 |  |  |  |  | 1 |  |  |  |  | 0.12 |  | 1 |  | 2
44 | Keonjhar | Patna | Patna | Tando | KED,Keonjhar | Patna | Banamahuldiha | 0.048 | 21 31 20.1 | 85 58 48.6 |  |  |  |  | 1 |  |  |  |  | 0.06 |  | 1 |  | 2
45 | Keonjhar | Patna | Patna | Tando | KED,Keonjhar | Patna | Rohiniduma | 0.047 | 21 30 19.9 | 86 0 7.1 |  |  |  |  | 1 |  |  |  |  | 0.05 |  | 1 |  | 2
46 | Keonjhar | Patna | Patna | Patna | KED,Keonjhar | Patna | Gobarabeda | 0.05 | 21 36 4.5 | 85 50 50.8 |  |  |  |  | 1 |  |  |  |  | 0.06 |  | 1 |  | 2
47 | Keonjhar | Patna | Patna | Patna | KED,Keonjhar | Patna | Madhapur | 0.05 | 21 37 49.5 | 85 51 44.4 |  |  |  |  | 1 |  |  |  |  | 0.06 |  | 1 |  | 2
48 | Keonjhar | Patna | Saharpada | Udayapur | KED,Keonjhar | Saharapada | Baikala Patnali | 0.05 | 21 45 1.3 | 85 53 17.2 |  |  |  |  | 1 |  |  |  |  | 0.06 |  | 1 |  | 2
49 | Keonjhar | Patna | Saharpada | Udayapur | KED,Keonjhar | Saharapada | Duaghat | 0.05 | 21 45 9.6 | 85 49 16.6 |  |  |  |  | 1 |  |  |  |  | 0.06 |  | 1 |  | 2
50 | Keonjhar | Patna | Saharpada | Machhagarh(N) | KED,Keonjhar | Saharapada | Kucheibeda | 0.5 | 21 42 38.7 | 86 2 55.9 |  |  |  |  | 5 |  |  |  |  | 0.55 |  | 5 |  | 10
51 | Keonjhar | Patna | Saharpada | Machhagarh(S) | KED,Keonjhar | Saharapada | Gohira | 0.3 | 21 37 6.4 | 86 0 35.5 |  |  |  |  | 3 |  |  |  |  | 0.33 |  | 3 |  | 6
52 | Keonjhar | Champua | Balibandha | Balibandha | KED,Keonjhar | Telkoi | Siriabahal | 1.0 | 21 54 49.6 | 85 34 06.3 |  |  |  |  | 16 |  |  |  |  | 1.1 | 3 | 16 |  | 32
53 | Keonjhar | Champua | Balibandha | Chipinda | KED,Keonjhar | Telkoi | Brahmanijhari | 0.4 | 21 51 58.3 | 85 29 53.5 |  |  |  |  | 4 |  |  |  |  | 0.44 |  | 4 |  | 8
54 | Keonjhar | Telkoi | Telkoi | Golabandha | KED,Keonjhar | Telkoi | Jagamohanpur Chhaka (Near Pandita Sir's house) | 0.1 | 21 26 1.7 | 85 19 29 |  |  |  |  | 1 |  |  |  |  | 0.11 |  | 1 |  | 2
55 | Keonjhar | Telkoi | Telkoi | Golabandha | KED,Keonjhar | Telkoi | Jagamohanpur to Keonjhar (NH Left side) | 0.1 | 21 26 2.7 | 85 19 28.8 |  |  |  |  | 1 |  |  |  |  | 0.11 |  | 1 |  | 2
56 | Keonjhar | Telkoi | Telkoi | Golabandha | KED,Keonjhar | Telkoi | Saruali Siba Mandira | 0.3 | 21 27 39.9 | 85 19 31.7 |  |  |  |  | 3 |  |  |  |  | 0.33 |  | 3 |  | 6
57 | Keonjhar | Telkoi | Telkoi | Golabandha | KED,Keonjhar | Telkoi | Jagamohanpur (Near ATM) | 0.5 | 21 25 57.3 | 85 19 24.2 | 3 | 1 | 1 |  | 5 |  |  |  |  | 0.55 |  | 8 |  | 10
58 | Keonjhar | Telkoi | Talapada | Oriya | KED,Keonjhar | Telkoi | Haladipani near village road side | 0.5 | 21 25 24.24 | 85 27 43.62 | 10 |  | 5 |  | 25 |  |  |  |  | 0.55 | 10 | 35 |  | 50 |  | 1
59 | Keonjhar | Telkoi | Talapada | SN Purgoda | KED,Keonjhar | Telkoi | Birda | 0.8 | 21 22 31.6 | 85 29 31.6 |  |  |  |  | 8 |  |  |  |  | 0.88 | 2 | 8 |  | 16
60 | Keonjhar | Telkoi | Talapada | SN Purgoda | KED,Keonjhar | Telkoi | Bhaliadala | 0.1 | 21 22 50.5 | 85 26 37.8 |  |  |  |  | 1 |  |  |  |  | 0.11 |  | 1 |  | 2
[8 empty] | 16.998 |  |  | 13 | 1 | 6 | 0 | 226 | 3 | 0 | 0 | 0 | 19.8815 | 37 | 239 | 0 | 458 | 0 | 2

## Package-28
PROPOSAL FOR STRENGTHENING OF ELECTRICAL NETWORK TO AVOID ELECTROCUTION OF ELEPHANTS UNDER KEONJHAR DISTRICT
SL No. | Forest Division | Forest Range | Forest Section | Forest Beat | Electrical Division | Electrical Section | Village | Stretch of transmission lines in Km. | GPS coordinates |  | Proposed Scope of Work
[9 empty] | Geo-Coordinate |  | LT Interposing Pole(With 9mtr RS Joist) ( in No.) | 3-Ph LT AB Cable (4x50+1x35+1x16mm2) ( in Km) | Fixing of 16mm LT Stay ( in Set) | 11 KV Interposing as per field requirement ( in No.) |  |  | 33KV Interposing as per field requirement ( in No.) |  |  | 11KV Insulated Conductor (99sqmm) in CKm | Fixing of 18mm HT Stay ( in Set) | Couping of Pole in No. | Fencing of Sub-station(in No.) | Spike (2nos. Per set per Pole) in Set | VCB
[9 empty] | Latitude | Longitude |  |  |  | 9 mtr RS Joist | 10 mtr Joist | 11 mtr Joist | 10 mtr Joist | 11 mtr Joist | 13 mtr RS Joist | [5 empty] | 33KV | 11KV
1 | Keonjhar | Keonjhar | Town | Maidankel | KED,Keonjhar | Turumunga | Maidankel | 0.6 | 21 40 7.67 | 85 42 35.07 |  |  |  |  | 15 |  |  |  |  | 0.66 |  | 15 |  | 30
2 | Keonjhar | Keonjhar | Town | Maidankel | KED,Keonjhar | Turumunga | Keri | 0.6 | 21 41 12.53 | 85 42 55.88 |  |  |  |  | 6 |  |  |  |  | 0.66 | 1 | 6 |  | 12
3 | Keonjhar | Patna | Saharpada | Raidiha | KED,Keonjhar | Turumunga | Rengalbeda | 0.05 | 21 38 17.1 | 85 57 20 |  |  |  |  | 1 |  |  |  |  | 0.05 |  | 1 |  | 2
4 | Keonjhar | Patna | Saharpada | Raidiha | KED,Keonjhar | Turumunga | Rengalbeda | 0.05 | 21 38 15 | 85 57 38 |  |  |  |  | 1 |  |  |  |  | 0.06 |  | 1 |  | 2
5 | Keonjhar | Patna | Saharpada | Raidiha | KED,Keonjhar | Turumunga | Katabeda | 0.05 | 21 37 11 | 85 57 8.3 |  |  |  |  | 1 |  |  |  |  | 0.05 |  | 1 |  | 2
6 | Keonjhar | Patna | Khireitangiri | Jamunaposi | KED,Keonjhar | Turumunga | Dalanga | 0.2 | 21 42 12.1 | 85 43 20 |  |  |  |  | 2 |  |  | 15 |  | 0.22 |  | 17 | 34 | 34
7 | Keonjhar | Patna | Khireitangiri | Jamunaposi | KED,Keonjhar | Turumunga | Jamunaposi | 0.3 | 21 42 40.4 | 85 45 7.4 | 6 | 0.24 | 2 |  | 6 |  |  |  |  | 0.33 |  | 12 |  | 12
8 | Keonjhar | Patna | Khireitangiri | Jamunaposi | KED,Keonjhar | Turumunga | Padmapur | 0.2 | 21 42 34.4 | 85 46 53.7 | 1 |  |  |  | 11 |  |  |  |  | 0.22 |  | 12 |  | 22
9 | Keonjhar | Patna | Khireitangiri | Rajnagar | KED,Keonjhar | Turumunga | Rajnagar | 0.4 | 21 45 51.3 | 85 49 14.7 | 5 |  |  |  | 6 |  |  |  |  | 0.44 |  | 11 |  | 12
10 | Keonjhar | Patna | Khireitangiri | Rajnagar | KED,Keonjhar | Turumunga | Nuagaon | 0.15 | 21 46 10 | 85 48 14.5 |  |  |  |  | 2 |  |  |  |  | 0.165 |  | 2 |  | 4
11 | Keonjhar | Patna | Khireitangiri | Rajnagar | KED,Keonjhar | Turumunga | Nuagaon | 0.3 | 21 46 28.2 | 85 48 24.7 |  |  |  |  | 3 |  |  |  |  | 0.33 |  | 3 |  | 6
12 | Keonjhar | Patna | Khireitangiri | Rajnagar | KED,Keonjhar | Turumunga | Barudiposi | 0.15 | 21 44 17.6 | 85 46 40.9 |  |  |  |  | 2 |  |  |  |  | 0.165 |  | 2 |  | 4
13 | Keonjhar | Patna | Khireitangiri | Rajnagar | KED,Keonjhar | Turumunga | Barudiposi | 0.6 | 21 44 1.8 | 85 46 38.5 |  |  |  |  | 6 |  |  |  |  | 0.66 | 1 | 6 |  | 12
14 | Keonjhar | Patna | Khireitangiri | Khireitangiri | KED,Keonjhar | Turumunga | Dudhiachua | 0.15 | 21 42 33.8 | 85 41 7.3 |  |  |  |  | 2 |  |  |  |  | 0.165 |  | 2 |  | 4
15 | Keonjhar | Patna | Khireitangiri | Khireitangiri | KED,Keonjhar | Turumunga | Bhurudiposi | 0.2 | 21 42 26.7 | 85 41 46 | 2 | 0.08 | 1 |  | 2 |  |  |  |  | 0.22 |  | 4 |  | 4
16 | Keonjhar | Patna | Khireitangiri | Khireitangiri | KED,Keonjhar | Turumunga | Bhulda | 0.6 | 21 44 10.7 | 85 41 14 | 3 | 0.12 | 1 |  | 6 |  |  |  |  | 0.66 |  | 9 |  | 12
17 | Keonjhar | Patna | Khireitangiri | Khireitangiri | KED,Keonjhar | Turumunga | Nischintpur | 0.15 | 21 45 10.3 | 85 41 42.9 |  |  |  |  | 2 |  |  |  |  | 0.165 |  | 2 |  | 4
18 | Keonjhar | Patna | Khireitangiri | Khireitangiri | KED,Keonjhar | Turumunga | Karanasahi | 0.3 | 21 44 6.7 | 85 43 26.9 |  |  |  |  | 3 |  |  |  |  | 0.33 |  | 3 |  | 6
19 | Keonjhar | Patna | Khireitangiri | Khireitangiri | KED,Keonjhar | Turumunga | Bandhanhara | 0.7 | 21 46 19 | 85 44 36 |  |  |  |  | 7 |  |  |  |  | 0.77 | 1 | 7 |  | 14
20 | Keonjhar | Patna | Khireitangiri | Tinda | KED,Keonjhar | Turumunga | Dumurigoda | 0.05 | 21 48 45.4 | 85 48 20.2 |  |  |  |  | 6 |  |  |  |  | 0.06 |  | 6 |  | 12
21 | Keonjhar | Patna | Khireitangiri | Tinda | KED,Keonjhar | Turumunga | Belaposi | 1 | 21 48 40.3 | 85 46 5.9 |  |  |  |  | 20 |  |  |  |  | 1.1 | 3 | 20 |  | 40
22 | Keonjhar | Patna | Khireitangiri | Tinda | KED,Keonjhar | Turumunga | Putugaon | 0.35 | 21 47 55.6 | 85 45 49.2 |  |  |  |  | 11 |  |  |  |  | 0.4 |  | 11 |  | 22
23 | Keonjhar | Patna | Khireitangiri | Tinda | KED,Keonjhar | Turumunga | Baliaposi | 0.8 | 21 46 18.8 | 85 45 35.1 |  |  |  |  | 8 |  |  |  |  | 0.88 | 2 | 8 |  | 16
24 | Keonjhar | Patna | Khireitangiri | Tinda | KED,Keonjhar | Turumunga | Chemena | 0.5 | 21 46 12.7 | 85 46 19.3 |  |  |  |  | 10 |  |  |  |  | 0.55 |  | 10 |  | 20
25 | Keonjhar | Champua | Ukunda | Jyotipur | KED,Keonjhar | Turumunga | Jyotipur | 0.5 | 21 52 38.9 | 85 47 38.1 | 4 |  | 1 |  | 5 |  |  |  |  | 0.55 |  | 9 |  | 10
26 | Keonjhar | Champua | Ukunda | Banika | KED,Keonjhar | Turumunga | Padua | 1.0 | 21 55 35.2 | 85 44 31.9 |  |  |  |  | 15 | 0 |  |  |  | 1.1 | 3 | 15 |  | 30
27 | Keonjhar | Champua | Ukunda | Jyotipur | KED,Keonjhar | Turumunga | Niundi | 1.9 | 21 52 47.5 | 85 46 19.4 |  |  |  |  | 19 |  |  |  |  | 2.1 | 4 | 19 |  | 38
28 | Keonjhar | Champua | Ukunda | Jyotipur | KED,Keonjhar | Turumunga | Padmapur | 1.5 | 21 55 23.6 | 85 46 50.2 |  |  |  |  | 15 |  |  |  |  | 1.65 | 3 | 15 |  | 30
29 | Keonjhar | Champua | Ukunda | Jyotipur | KED,Keonjhar | Turumunga | Rengalgoda | 1.6 | 21 56 48.9 | 85 47 7.3 |  |  |  |  | 16 |  |  |  |  | 1.76 | 3 | 16 |  | 32
30 | Keonjhar | Champua | Ukunda | Jyotipur | KED,Keonjhar | Turumunga | Maliposi | 1.1 | 21 54 48.1 | 85 46 15.8 |  |  |  |  | 11 |  |  |  |  | 1.21 | 2 | 11 |  | 22
31 | Keonjhar | Champua | Ukunda | Jyotipur | KED,Keonjhar | Turumunga | Kemudia | 0.4 | 21 56 57 | 85 46 45.1 |  |  |  |  | 8 |  |  |  |  | 0.44 |  | 8 |  | 16
[8 empty] | 15.45 | 0 | 0 | 21 | 0.44 | 5 | 0 | 228 | 0 | 0 | 15 | 0 | 18.12 | 23 | 264 | 34 | 486 | 0 | 0

## Package-29
PROPOSAL FOR STRENGTHENING OF ELECTRICAL NETWORK TO AVOID ELECTROCUTION OF ELEPHANTS UNDER KEONJHAR DISTRICT
SL No. | Forest Division | Forest Range | Forest Section | Forest Beat | Electrical Division | Electrical Section | Village | Stretch of transmission lines in Km. | GPS coordinates |  | Proposed Scope of Work
[9 empty] | Geo-Coordinate |  | LT Interposing Pole(With 9mtr RS Joist) ( in No.) | 3-Ph LT AB Cable (4x50+1x35+1x16mm2) ( in Km) | Fixing of 16mm LT Stay ( in Set) | 11 KV Interposing as per field requirement ( in No.) |  |  | 33KV Interposing as per field requirement ( in No.) |  |  | 11KV Insulated Conductor (99sqmm) in CKm | Fixing of 18mm HT Stay ( in Set) | Couping of Pole in No. | Fencing of Sub-station(in No.) | Spike (2nos. Per set per Pole) in Set | VCB
[9 empty] | Latitude | Longitude |  |  |  | 9 mtr RS Joist | 10 mtr Joist | 11 mtr Joist | 10 mtr Joist | 11 mtr Joist | 13 mtr RS Joist | [5 empty] | 33KV | 11KV
1 | Keonjhar | Keonjhar | Naranpur | Gopalpur(W) | AED,Anandapur | Dhenkikote | Chandapasi | 0.2 | 21 33 24.7 | 85 43 17.0 |  |  |  |  | 2 |  |  |  |  | 0.22 |  | 2 |  | 4
2 | Keonjhar | Keonjhar | Naranpur | Gopalpur(W) | AED,Anandapur | Dhenkikote | Jharbeda | 0.5 | 21 32 12.3 | 85 43 40.5 |  |  |  |  | 5 |  |  |  |  | 0.55 | 1 | 5 |  | 10
3 | Keonjhar | Keonjhar | Naranpur | Gopalpur(W) | AED,Anandapur | Dhenkikote | Jharbeda | 2 | 21 32 10.6 | 85 43 06.3 |  |  |  |  | 15 |  |  |  |  | 2.2 | 5 | 15 |  | 30
4 | Keonjhar | Keonjhar | Naranpur | Gopalpur(W) | AED,Anandapur | Dhenkikote | Sarupat | 0.5 | 21 31 06.7 | 85 42 52.5 |  |  |  |  | 5 |  |  |  |  | 0.55 | 2 | 5 |  | 10
5 | Keonjhar | Keonjhar | Naranpur | Naranpur | AED,Anandapur | Dhenkikote | Jamunalia | 0.1 | 21 35 14.3 | 85 39 25.0 |  |  |  |  | 1 |  |  |  |  | 0.11 |  | 1 |  | 2
6 | Keonjhar | Keonjhar | Naranpur | Naranpur | AED,Anandapur | Dhenkikote | Ramachandrapur | 0.1 | 21 35 00.9 | 85 39 10.9 |  |  |  |  | 5 |  |  |  |  | 0.11 | 3 | 5 |  | 10
7 | Keonjhar | Keonjhar | Naranpur | Naranpur | AED,Anandapur | Dhenkikote | Ramachandrapur | 0.1 | 21 34 52.8 | 85 39 06.5 |  |  |  |  | 6 |  |  |  |  | 0.11 | 3 | 6 |  | 12
8 | Keonjhar | Keonjhar | Naranpur | Naranpur | AED,Anandapur | Dhenkikote | Ukuchabeda | 0.1 | 21 33 37.2 | 85 39 42.4 |  |  |  |  | 9 |  |  |  |  | 0.11 | 6 | 9 |  | 18
9 | Keonjhar | Keonjhar | Naranpur | Naranpur | AED,Anandapur | Dhenkikote | Baiganposi | 0.1 | 21 38 11.0 | 85 39 54.9 |  |  |  |  | 1 |  |  |  |  | 0.11 |  | 1 |  | 2
10 | Keonjhar | Keonjhar | Naranpur | Balabhadrapur | AED,Anandapur | Dhenkikote | Balabhadrapur | 0.3 | 21 30 00.5 | 85 4059.2 |  |  |  |  | 15 |  |  |  |  | 0.33 | 6 | 15 |  | 30
11 | Keonjhar | Keonjhar | Naranpur | Raghunathpur | AED,Anandapur | Dhenkikote | Dimirmunda | 0.1 | 21 37 54.9 | 85 41 04.6 |  |  |  |  | 1 |  |  |  |  | 0.11 |  | 1 |  | 2
12 | Keonjhar | Keonjhar | Naranpur | Raghunathpur | AED,Anandapur | Dhenkikote | Kajaleipasi | 0.5 | 21 38 25.3 | 85 43 12.8 |  |  |  |  | 5 |  |  |  |  | 0.55 |  | 5 |  | 10
13 | Keonjhar | Keonjhar | Naranpur | Raghunathpur | AED,Anandapur | Dhenkikote | Kajaleipasi | 2 | 21 37 52.0 | 85 44 15.1 |  |  |  |  | 17 |  |  |  |  | 2.2 | 4 | 17 |  | 34
14 | Keonjhar | Keonjhar | Naranpur | Raghunathpur | AED,Anandapur | Dhenkikote | Kajaleipasi | 0.3 | 21 3740.8 | 85 44 24.3 |  |  |  |  | 3 |  |  |  |  | 0.33 |  | 3 |  | 6
15 | Keonjhar | Keonjhar | Naranpur | Raghunathpur | AED,Anandapur | Dhenkikote | Kajaleipasi | 0.5 | 21 37 51.2 | 85 44 29.2 |  |  |  |  | 5 |  |  |  |  | 0.55 | 1 | 5 |  | 10
16 | Keonjhar | Keonjhar | Naranpur | Raghunathpur | AED,Anandapur | Dhenkikote | Haladharpur | 0.3 | 21 37 39.9 | 85 44 50.8 |  |  |  |  | 3 |  |  |  |  | 0.33 |  | 3 |  | 6
17 | Keonjhar | Keonjhar | Naranpur | Raghunathpur | AED,Anandapur | Dhenkikote | Jajapasi | 0.2 | 21 37 48.0 | 85 45 10.8 |  |  |  |  | 2 |  |  |  |  | 0.22 |  | 2 |  | 4
18 | Keonjhar | Keonjhar | Naranpur | Raghunathpur | AED,Anandapur | Dhenkikote | Dumuria | 0.2 | 21 38 15.8 | 85 46 15.4 |  |  |  |  | 2 |  |  |  |  | 0.22 |  | 2 |  | 4
19 | Keonjhar | Keonjhar | Naranpur | Raghunathpur | AED,Anandapur | Dhenkikote | Dumuria | 0.2 | 2138 13.7 | 85 45 58.6 |  |  |  |  | 2 |  |  |  |  | 0.22 |  | 2 |  | 4
20 | Keonjhar | Keonjhar | Naranpur | Raghunathpur | AED,Anandapur | Dhenkikote | Haladharpur | 0.3 | 21 37 21.9 | 85 44 44.4 |  |  |  |  | 3 |  |  |  |  | 0.33 |  | 3 |  | 6
21 | Keonjhar | Keonjhar | Naranpur | Raghunathpur | AED,Anandapur | Dhenkikote | Haladharpur | 0.2 | 21 37 26.9 | 85 44 39.1 |  |  |  |  | 2 |  |  |  |  | 0.22 |  | 2 |  | 4
22 | Keonjhar | Keonjhar | Naranpur | Raghunathpur | AED,Anandapur | Dhenkikote | Majurpasi | 0.3 | 21 36 01.0 | 85 44 21.4 |  |  |  |  | 3 |  |  |  |  | 0.33 |  | 3 |  | 6
23 | Keonjhar | Keonjhar | Naranpur | Raghunathpur | AED,Anandapur | Dhenkikote | Majurpasi | 0.2 | 21 35 56.8 | 85 44 18.8 |  |  |  |  | 2 |  |  |  |  | 0.22 |  | 2 |  | 4
24 | Keonjhar | Keonjhar | Naranpur | Gopalpur(E) | AED,Anandapur | Dhenkikote | Asanbani | 0.3 | 2131 42.8 | 85 45 08.6 |  |  |  |  | 3 |  |  |  |  | 0.33 |  | 3 |  | 6
25 | Keonjhar | Keonjhar | Naranpur | Gopalpur(E) | AED,Anandapur | Dhenkikote | Bankapatuli | 0.1 | 21 33 45.1 | 85 44 33.8 |  |  |  |  | 1 |  |  |  |  | 0.11 |  | 1 |  | 2
26 | Keonjhar | Keonjhar | Naranpur | Gopalpur(E) | AED,Anandapur | Dhenkikote | Baliadihasahi | 0.4 | 21 31 31.8 | 85 43 36.5 |  |  |  |  | 4 |  |  |  |  | 0.44 |  | 4 |  | 8
27 | Keonjhar | Keonjhar | Naranpur | Gopalpur(E) | AED,Anandapur | Dhenkikote | Badabarbeda | 0.1 | 21 29 36.5 | 85 44 33.7 |  |  |  |  | 1 |  |  |  |  | 0.11 |  | 1 |  | 2
28 | Keonjhar | Keonjhar | Janghira | Janghira(E) | AED,Anandapur | Dhenkikote | Masinabilla | 0.2 | 21 26 41.1 | 85 38 23.1 |  |  |  |  | 2 |  |  |  |  | 0.22 |  | 2 |  | 4
29 | Keonjhar | Keonjhar | Janghira | Janghira(W) | AED,Anandapur | Dhenkikote | Dumuria | 0.2 | 21 27 45.1 | 85 34 23.8 |  |  |  |  | 4 |  |  |  |  | 0.22 |  | 4 |  | 8
30 | Keonjhar | Ghatgaon | Ghatgaon | Kolimati | AED,Anandapur | Ghasipura | Colony Sahi (Kanto) | 1.5 | 21 19 19.9 | 86 1 54.5 |  |  |  |  | 13 |  |  |  |  | 1.65 | 3 | 13 |  | 26
31 | Keonjhar | Ghatgaon | Ghatgaon | Kolimati | AED,Anandapur | Ghasipura | Badasahi | 2 | 21 19 8.7 | 86 1 37 |  |  |  |  | 18 |  |  |  |  | 2.2 | 4 | 18 |  | 36
32 | Keonjhar | Ghatgaon | Dhenkikote | Dhenkikote | AED,Anandapur | Dhenkikote | Khajurijuani | 1.5 | 21 31 37.6 | 85 48 39.9 |  |  |  |  | 12 |  |  | 15 |  | 1.65 | 9 | 27 |  | 54
[8 empty] | 15.6 | 0 | 0 | 0 | 0 | 0 | 0 | 172 | 0 | 0 | 15 | 0 | 17.16 | 47 | 187 | 0 | 374 | 0 | 0

## Package-30
PROPOSAL FOR STRENGTHENING OF ELECTRICAL NETWORK TO AVOID ELECTROCUTION OF ELEPHANTS UNDER KEONJHAR DISTRICT
SL No. | Forest Division | Forest Range | Forest Section | Forest Beat | Electrical Division | Electrical Section | Village | Stretch of transmission lines in Km. | GPS coordinates |  | Proposed Scope of Work
[9 empty] | Geo-Coordinate |  | LT Interposing Pole(With 9mtr RS Joist) ( in No.) | 3-Ph LT AB Cable (4x50+1x35+1x16mm2) ( in Km) | Fixing of 16mm LT Stay ( in Set) | 11 KV Interposing as per field requirement ( in No.) |  |  | 33KV Interposing as per field requirement ( in No.) |  |  | 11KV Insulated Conductor (99sqmm) in CKm | Fixing of 18mm HT Stay ( in Set) | Couping of Pole in No. | Fencing of Sub-station(in No.) | Spike (2nos. Per set per Pole) in Set | VCB
[9 empty] | Latitude | Longitude |  |  |  | 9 mtr RS Joist | 10 mtr Joist | 11 mtr Joist | 10 mtr Joist | 11 mtr Joist | 13 mtr RS Joist | [5 empty] | 33KV | 11KV
1 | Keonjhar | Ghatgaon | Dhenkikote | Pipilia | AED,Anandapur | Dhenkikote | Pipilia | 0.5 | 21 33 44.7 | 85 45 57.1 |  |  |  |  | 5 |  |  |  |  | 0.55 |  | 5 |  | 10
2 | Keonjhar | Ghatgaon | Dhenkikote | Pipilia | AED,Anandapur | Dhenkikote | Pipilia -Asanbani road | 1.5 | 21 32 57.3 | 85 45 43.2 |  |  |  |  | 14 |  |  |  |  | 1.65 | 3 | 14 |  | 28
3 | Keonjhar | Ghatgaon | Dhenkikote | Dhenkikote | AED,Anandapur | Dhenkikote | Monaharpur to Danguaposi road | 2 | 21 31 16.2 | 85 46 35.4 |  |  |  |  | 17 |  |  |  |  | 2.2 | 3 | 17 |  | 34
4 | Keonjhar | Ghatgaon | Dhenkikote | Dhenkikote | AED,Anandapur | Dhenkikote | Tandibeda to joirasandha | 2 | 21 30 38.1 | 85 47 59.2 |  |  |  |  | 18 |  |  |  |  | 2.2 | 4 | 18 |  | 36
5 | Keonjhar | Ghatgaon | Dhenkikote | Dhenkikote | AED,Anandapur | Dhenkikote | Tandibeda | 1 | 21 30 23.4 | 85 48 10.6 |  |  |  |  | 10 |  |  |  |  | 1.1 | 2 | 10 |  | 20
6 | Keonjhar | Ghatgaon | Dhenkikote | Dhenkikote | AED,Anandapur | Dhenkikote | Tandibeda to Mahulagadia road | 1 | 21 30 22.3 | 85 48 30.5 |  |  |  |  | 10 |  |  |  |  | 1.1 | 3 | 10 |  | 20
7 | Keonjhar | Ghatgaon | Dhenkikote | Dhenkikote | AED,Anandapur | Dhenkikote | Mahulagadia | 0.5 | 21 30 0.2 | 85 49 6.7 |  |  |  |  | 5 |  |  |  |  | 0.55 |  | 5 |  | 10
8 | Keonjhar | Ghatgaon | Dhenkikote | Dhenkikote | AED,Anandapur | Dhenkikote | Raibani | 1 | 21 28 34.3 | 85 50 7 |  |  |  |  | 10 |  |  |  |  | 1.1 | 2 | 10 |  | 20
9 | Keonjhar | Ghatgaon | Dhenkikote | Dhenkikote | AED,Anandapur | Dhenkikote | Raibani to santrapur road | 1 | 21 28 3.2 | 85 49 49.1 |  |  |  |  | 10 |  |  | 4 |  | 1.1 | 4 | 14 |  | 28
10 | Keonjhar | Ghatgaon | Dhenkikote | Dhenkikote | AED,Anandapur | Dhenkikote | Nusuriposi | 1 | 21 26 27.8 | 85 48 28 |  |  |  |  | 10 |  |  | 4 |  | 1.1 | 4 | 14 |  | 28
11 | Keonjhar | Ghatgaon | Dhenkikote | Dhenkikote | AED,Anandapur | Dhenkikote | Dehuripada | 1 | 21 25 41.6 | 85 48 12.4 | 3 |  |  |  | 10 |  |  |  |  | 1.1 | 4 | 13 |  | 20
12 | Keonjhar | Ghatgaon | Deobandha | Raghubeda | AED,Anandapur | Dhenkikote | Raghubeda to Gandasila | 1 | 21 28 54.2 | 85 47 4.3 |  |  |  |  | 10 |  |  |  |  | 1.1 | 5 | 10 |  | 20
13 | Keonjhar | Ghatgaon | Deobandha | Deobandh | AED,Anandapur | Dhenkikote | Binida | 0.5 | 21 25 6.3 | 85 42 20.8 |  |  |  |  | 5 |  |  |  |  | 0.55 |  | 5 |  | 10
14 | Keonjhar | Ghatgaon | Deobandha | Deobandh | AED,Anandapur | Dhenkikote | Deobandh high school | 0.5 | 21 26 6.6 | 85 43 3.2 |  |  |  |  | 5 |  |  |  |  | 0.55 |  | 5 |  | 10
15 | Keonjhar | Ghatgaon | Deobandha | Deobandh | AED,Anandapur | Dhenkikote | Patabari | 0.5 | 21 27 2.3 | 85 44 8.2 |  |  |  |  | 5 |  |  |  |  | 0.55 |  | 5 |  | 10
[8 empty] | 15 | 0 | 0 | 3 | 0 | 0 | 0 | 144 | 0 | 0 | 8 | 0 | 16.5 | 34 | 155 | 0 | 304 | 0 | 0

## Package-31
PROPOSAL FOR STRENGTHENING OF ELECTRICAL NETWORK TO AVOID ELECTROCUTION OF ELEPHANTS UNDER KEONJHAR DISTRICT
SL No. | Forest Division | Forest Range | Forest Section | Forest Beat | Electrical Division | Electrical Section | Village | Stretch of transmission lines in Km. | GPS coordinates |  | Proposed Scope of Work
[9 empty] | Geo-Coordinate |  | LT Interposing Pole(With 9mtr Joist) ( in No.) | 3-Ph LT AB Cable (3x50+1x35+1x16mm2) ( in Km) | Fixing of 16mm LT Stay ( in Set) | 11 KV Interposing as per field requirement ( in No.) |  |  | 33KV Interposing as per field requirement ( in No.) |  |  | 11KV Insulated Conductor (99sqmm) in CKm | Fixing of 18mm HT Stay ( in Set) | Couping of Pole in No. | Fencing of Sub-station(in No.) | Spike(2nos. Per set per Pole) in No. | VCB
[9 empty] | Latitude | Longitude |  |  |  | 9 mtr Joist | 10 mtr Joist | 11 mtr Joist | 10 mtr Joist | 11 mtr Joist | 13 mtr RS Joist | [5 empty] | 33KV | 11KV
1 | Keonjhar WL | Hadagarh | Hadagarh | Hadagarh | AED,Anandapur | Bidyadharpur | Hadagarh To Bidyadharpur | 6.2 | 21 17 1.62 | 86 17 48.57 | 12 | 3.8 | 12 |  | 12 | [5 empty] | 5 | 12 |  | 24
2 | Keonjhar WL | [7 empty] | 21 14 10.64 | 86 18 21.44 | 13 | 1.52 | 13 | [8 empty] | 13 |  | 0
3 | Keonjhar WL | [7 empty] | 21 14 0.02 | 86 18 45.42 | 10 | 1.54 | 10 | [8 empty] | 10 |  | 0
4 | Keonjhar WL | Hadagarh | Hadagarh | Hadagarh | AED,Anandapur | Bidyadharpur | Bidyadharpur To Kusatikiri | 6.64 | 21 14 0.02 | 86 18 45.42 | 8 | 2.35 | 8 |  | 6 | [6 empty] | 8 |  | 12
5 | Keonjhar WL | [7 empty] | 21 14 51.92 | 86 19 4.64 | 17 | 1.32 | 17 |  | 7 | [6 empty] | 17 |  | 14
6 | Keonjhar WL | [7 empty] | 21 15 53.01 | 86 19 50.24 | 9 | 1.58 | 9 |  | 5 | [6 empty] | 9 |  | 10
7 | Keonjhar WL | [7 empty] | 21 16 18.76 | 86 18 35.89 | 11 | 2.2 | 11 |  | 2 | [6 empty] | 11 |  | 4
8 | Keonjhar WL | Hadagarh | Hadagarh | Hadagarh | AED,Anandapur | Bidyadharpur | Kusatikiri To Chanchalpada | 0.7 | 21 16 18.76 | 86 18 35.89 | 5 | 0.45 | 5 | [8 empty] | 5 |  | 0
9 | Keonjhar WL | [7 empty] | 21 16 39.18 | 86 18 24.61 | 4 | 0.38 | 4 | [8 empty] | 4 |  | 0
10 | Keonjhar WL | Hadagarh | Hadagarh | Hadagarh | AED,Anandapur | Bidyadharpur | Sankatapalia | 1.38 | 21 15 41.91 | 86 17 15.88 | 2 | 1.2 | 2 | [8 empty] | 2 |  | 0
11 | Keonjhar WL | [7 empty] | 21 15 43.10 | 86 18 03.61 | 2 | 0.318 | 2 | [8 empty] | 2 |  | 0
12 | Keonjhar WL | Hadagarh | Hadagarh | Hadagarh | AED,Anandapur | Bidyadharpur | Madhuban | 0.5 | 21 15 48.42 | 86 18 19.99 | 3 | 0.36 | 3 | [8 empty] | 3 |  | 0
13 | Keonjhar WL | [7 empty] | 21 15 50.12 | 86 18 02.21 | 2 | 0.28 | 2 | [8 empty] | 1 |  | 0
14 | Keonjhar WL | Hadagarh | Hadagarh | Hadagarh | AED,Anandapur | Bidyadharpur | Haradabadi | 0.7 | 21 15 34.63 | 86 18 5.37 | 1 | 0.77 | 1 |  | 15 | [5 empty] | 8 | 1 |  | 30
15 | Keonjhar WL | [7 empty] | 21 15 35.93 | 86 18 29.01 | 1 | 0 | 1 | [8 empty] | 1 |  | 0
16 | Keonjhar WL | Hadagarh | Hadagarh | Hadagarh | AED,Anandapur | Bidyadharpur | Sankhana To Bangore | 3.5 | 21 15 42.51 | 86 18 38.95 | 12 | 3.85 | 12 | [8 empty] | 12 |  | 0
17 | Keonjhar WL | [7 empty] | 21 15 54.45 | 86 20 32.67 | 11 | 0 | 11 | [8 empty] | 11 |  | 0
18 | Keonjhar WL | Hadagarh | Hadagarh | Baniapanka | AED,Anandapur | Bidyadharpur | Bangore To Balibarei | 3.5 | 21 15 54.45 | 86 20 32.67 | 11 | 3.85 | 11 |  | 10 | [5 empty] | 3 | 11 |  | 20
19 | Keonjhar WL | [7 empty] | 21 14 19.40 | 86 21 35.45 | 10 | 0 | 10 | [8 empty] | 10 |  | 0
20 | Keonjhar WL | Hadagarh | Hadagarh | Baniapanka | AED,Anandapur | Bidyadharpur | Bangore To Dhanurjaypur | 1.5 | 21 15 54.45 | 86 20 32.67 | 5 | 1.65 | 5 | [8 empty] | 5 |  | 0
21 | Keonjhar WL | [7 empty] | 21 16 38.10 | 86 21 11.30 | 9 | 0 | 9 | [8 empty] | 9 |  | 0
22 | Keonjhar WL | Hadagarh | Hadagarh | Baniapanka | AED,Anandapur | Bidyadharpur | Dhanurjaypur To Nuaragudi | 1 | 21 16 38.10 | 86 21 11.30 | 5 | 1.1 | 5 | [8 empty] | 5 |  | 0
23 | Keonjhar WL | [7 empty] | 21 16 28.38 | 86 21 45.22 | 2 | 0 | 2 | [8 empty] | 2 |  | 0
24 | Keonjhar WL | Hadagarh | Hadagarh | Baniapanka | AED,Anandapur | Bidyadharpur | Balibarei To Aturkana | 2 | 21 14 19.40 | 86 21 35.45 | 4 | 2.2 | 4 |  | 10 | [5 empty] | 3 | 4 |  | 20
25 | Keonjhar WL | [7 empty] | 21 15 08.45 | 86 20 52.62 | 7 | 0 | 7 | [8 empty] | 7 |  | 0
26 | Keonjhar WL | Hadagarh | Hadagarh | Baniapanka | AED,Anandapur | Bidyadharpur | Baniapnka To Jadabanka | 1 | 21 15 49.47 | 86 22 14.19 | 2 | 1.1 | 2 | [8 empty] | 2 |  | 0
27 | Keonjhar WL | [7 empty] | 21 16 21.68 | 86 22 16.76 | 3 | 0 | 3 | [8 empty] | 3 |  | 0
28 | Keonjhar WL | Hadagarh | Hadagarh | Baniapanka | AED,Anandapur | Bidyadharpur | Jadabanka To Tanla | 1 | 21 16 21.68 | 86 22 16.76 | 1 | 1.1 | 1 | [8 empty] | 1 |  | 0
29 | Keonjhar WL | [7 empty] | 21 16 40.72 | 86 21 45.63 | 2 | 0 | 2 | [8 empty] | 2 |  | 0
30 | Keonjhar WL | Hadagarh | Hadagarh | Baniapanka | AED,Anandapur | Bidyadharpur | Aturkana To Padhiaripalli | 1.6 | 21 15 08.45 | 86 20 52.62 | 5 | 1.76 | 5 |  | 5 | [5 empty] | 2 | 5 |  | 10
31 | Keonjhar WL | [7 empty] | 21 15 20.12 | 86 21 54.47 | 3 | 0 | 3 | [8 empty] | 3 |  | 0
[8 empty] | 31.22 | 0 | 0 | 192 | 34.678 | 192 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 21 | 191 | 0 | 144 | 0 | 0